## Tracker
WBS No. / SQ No. | Customer / Project Name | Application Type | Planning Officer | Officer Email | Status | Last Status Change | SLA Days | Days Pending | Days vs SLA | Submission Round | Paid | Paid Date | Budget Assigned | Priority | Remarks
SIB-260001 | Example A - Housing Ph2 | Turnkey Stage 2 | ABC | officer@example.com | Rejected - Pending Resubmission | 2026-07-28 | 10 | 6 | -4 | 2nd | Yes | 2026-07-30 | No | HIGH - ASSIGN BUDGET | Paid, budget not yet assigned (EXAMPLE ROW)
SIB260002 | Example B - Kpg Supply | Supply Application (<100kW) | DEF | officer@example.com | Cost Submitted | 2026-08-02 | 12 | 1 | -11 | 1st | No |  | No | OK | (EXAMPLE ROW)
SQ5401 | Example C - Commercial Lot | Upgrading/Downgrading of Supply | GHI | officer@example.com | Charge Issued | 2026-07-24 | 14 | 10 | -4 | 1st | No |  | No | AWAITING PAYMENT | Awaiting customer payment (EXAMPLE ROW)
SIB-260004 | Example D - Quarry Access | Turnkey Stage 1 | JKL | officer@example.com | Keyed into SAP | 2026-07-19 | 10 | 15 | 5 | 3rd | No |  | No | OVERDUE - ESCALATE | Past SLA, third round (EXAMPLE ROW)
Formulas:
Days Pending = IF([WBS No. / SQ No.]="","",IF([Last Status Change]="","",TODAY()-[Last Status Change]))

## Settings
Setting | Days
Paid project - chase after (days pending) | 2
"Due soon" warning - days before SLA | 2
Escalate - days past SLA | 3
Default SLA days (used when SLA Days is blank) | 12
Yellow cells are inputs - change these anytime, no flow changes needed.

## Read Me
SESCO Planning - Connection Charge Tracker (intern project)
HEADER COLOURS
Dark blue = you fill in. Green = filled automatically by Power Automate. Grey = formula, do not type over.
PRIORITY (most urgent first)
HIGH - ASSIGN BUDGET (RED) - customer paid, Budget Assigned is not Yes. Money sits in CC-Suspense until done.
HIGH - PAID (RED) - customer has paid. Paid projects are always high priority.
OVERDUE - ESCALATE - past SLA by more than the escalation threshold.
OVERDUE - past its SLA date. DUE SOON - approaching its SLA date.
AWAITING PAYMENT - charge issued, customer has not paid. No action needed from the team.
OK - within SLA. SET DATE - Last Status Change is empty, please fill it.
NEW ROWS
Days Pending, Days vs SLA and Priority are table calculated columns - they fill in automatically
when you add a row. Do not type over them.
SLA DAYS
Mirrors the team sheet's '10/12 days' column. Enter the number governing that project (10, 12 or 14).
If left blank, the Settings sheet default is used.
ASSUMPTIONS TO CONFIRM
1. STA(P) - assumed to be the reviewing party Planning submits to. Nothing here depends on it.
2. Confirm what 10/12/14 represent, and whether they are calendar or working days (currently calendar).
3. Settings thresholds are placeholders - agree real numbers with the team.
DATA NOTE
All example rows are invented. Delete them before real use.
Keep genuine customer data out of anything sent to personal or external accounts.